## Miguel Chateloin
| Day of Week | Date | Check In | Check Out | Lunch In | Lunch Out | Short description of your work | Daily Hours | Weekly Hours | Overtime Hours | Approval
0 | 1
| Saturday | 2016-08-20 | [5 empty] | 0:00
| Sunday | 2016-08-21 | [5 empty] | 3:00
| Monday | 2016-08-22 | [5 empty] | 0:00
| Tuesday | 2016-08-23 | 9:00 | 14:00 | 12:00 | 13:00 | Wrote preliminary user stories | 4:00
| Wednesday | 2016-08-24 | 9:00 | 16:00 | 13:00 | 14:00 | Started setting up native ARDrone SDK, tested Drone flight, set up Android Environment, drafted install guides | 6:00
| Thursday | 2016-08-25 | 9:00 | 18:00 | 12:00 | 13:00 | Finished setting up Android Environment, update guides, started development on prototype application to test basic features of the ARDrone | 8:00
| Friday | 2016-08-26 | 9:00 | 12:30 | 0:00 | 0:00 | Reviewed new guidelines, edited all official project Drive documents for compliance, tested new RCA tablet with Android Lollipop 5, debugged an error that prevented running applications on the physical device, updated install guides to reflect these issues. | 3:30
1 | 2 | [6 empty] | 0:00
| Saturday | 2016-08-27 | [5 empty] | 0:00
| Sunday | 2016-08-28 | 11:00 | 14:00 |  |  | Continued debugging a device-related permissions issue which is currently preventing APK installation on the RCA Voyager Tablet. | 3:00
| Monday | 2016-08-29 | [5 empty] | 0:00
| Tuesday | 2016-08-30 | 9:45 | 17:00 | 11:30 | 15:00 | Attempted ROM reinstall on bricked device. No luck. Getting a refund on it. | 3:45
| Wednesday | 2016-08-31 | 10:30 | 17:00 | 12:00 | 13:00 | Studied react UI development and began creating prototype application, finally successfully installed to a Samsung Galaxy Tab 4. Performed indoor test flights for the drone using the python library Leonardo recommended. | 5:30
| Thursday | 2016-09-01 | 11:00 | 20:00 | 13:00 | 14:00 | Built a prototype Android UI for drawing a flight path on a Google Map. Tested ARDrone 1.0 Python library with ARDrone 1.0 indoors. Test flight drone in vacant field, controlled via machine. | 8:00
| Friday | 2016-09-02 | 11:00 | 16:00 | 13:00 | 14:00 | Met with product owner sprint review, retrospective, and scheduling for drone flights over crops. Worked on pulling more navdata, images and video from the drone. Forked an ARDrone 1.0 Python library to update it for compatibility with ARDrone 2.0 | 4:00
| 3 | [6 empty] | 0:00
| Saturday | 2016-09-03 | 17:30 | 20:00 |  |  | Set up a new off-the-shelf tool to pilot the drone. Flew outside EC. Recorded the data I needed. Prepared prototype materials, screenshots and videos of Android app and flight for Wagner and Mohsen. | 2:30
| Sunday | 2016-09-04 | [5 empty] | 0:00
| Monday | 2016-09-05 | [5 empty] | 0:00
| Tuesday | 2016-09-06 | 11:30 | 16:00 |  |  | Worked on merging Parrots Free Flight application's codebase with our current codebase containing the React Native Android setup. | 4:30
| Wednesday | 2016-09-07 | 8:00 | 18:00 | 1:00 | 2:00 | Switched to a better library for AR Drone 2.0, add scripted flight and piloted flight code to repository, piloted drone at Engineering Campus lot and took 3rd and 1st person video, navdata readings, confirming that we could in fact pull GPS off the drone. | 9:00
| Thusday | 2016-09-08 | 12:00 | 18:00 |  |  | Read through relevant parts of the AR Drone SDK and the Free Flight application, focused on learning interaction between the Android Activity interface and drone controller services. Did research on other Java based APIs that communicate with the drone over the network. Skimmed papers on autonomous drones. | 6:00
| Friday | 2016-09-09 | [5 empty] | 0:00
2 | 4 | [6 empty] | 0:00
| Saturday | 2016-09-10 | [5 empty] | 0:00
| Sunday | 2016-09-11 | [5 empty] | 0:00
| Monday | 2016-09-12 | 8:23 | 12:05 | 13:34 | 16:55 | Continued troubleshooting, working toward a successful build. System design meetings with team. | 0:21
| Tuesday | 2016-09-13 | 9:41 | 12:45 | 13:12 | 17:26 | Continued troubleshooting, working toward a successful build. System design meetings with team. | -0.048611
| Wednesday | 2016-09-14 | 8:52 | 10:43 | 12:18 | 17:06 | Continued troubleshooting, working toward a successful build. System design meetings with team. | -0.12292
| Thusday | 2016-09-15 | 9:40 | 23:50 | 13:12 | 15:16 | Continued troubleshooting, working toward a successful build. System design meetings with team. | 12:06
| Friday | 2016-09-16 | 10:40 | 13:23 |  |  | Continued troubleshooting, working toward a successful build. | 2:43
| 5 | [6 empty] | 0:00
| Saturday | 2016-09-17 | [5 empty] | 0:00
| Sunday | 2016-09-18 | [5 empty] | 0:00
| Monday | 2016-09-19 | 8:52 | 10:43 |  |  | Continued troubleshooting, working toward a successful build. | 1:51
| Tuesday | 2016-09-20 | 9:04 | 23:29 | 13:12 | 16:18 | Continued troubleshooting, working toward a successful build. | 11:19
| Wednesday | 2016-09-21 | 7:00 | 16:00 |  |  | Finalized architectural choice for drone SDK. Troubleshooted integration between ARDrone SDK service layer and React Native | 9:00
| Thusday | 2016-09-22 | 9:00 | 15:00 | 10:00 | 11:30 | Continued troubleshooting, working toward a successful build, created a separate repository to attempt a different project directory structure and build configuration. | 4:30
| Friday | 2016-09-23 | 14:30 | 19:30 |  |  | Met for biweekly SCRUM with product owner. Continued troubleshooting and finally got a successful build. Troubleshooted runtime errors due to React-Native related bundling issues. Got react-native enabled application to launch with the loaded AR Drone SDK. Next step is to write code to connect to the drone and start printing out navdata directly in Android. | 5:00
3 | 6 | [6 empty] | 0:00
| Saturday | 2016-09-24 | 17:00 | 21:00 |  |  | Update Sprint board with time card notes from past weeks. Improved user story phrasing. | 4:00
| Sunday | 2016-09-25 |  |  |  |  | No progress today, family outing. | 0:00
| Monday | 2016-09-26 | 7:06 | 8:00 | 10:00 | 18:00 | Worked on implementating #130
| Tuesday | 2016-09-27 | 7:23 | 13:00 | 14:23 | 19:00 | Worked on implementating #130 | 1:00
| Wednesday | 2016-09-28 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Thusday | 2016-09-29 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Friday | 2016-09-30 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| 7 | [5 empty] | Worked on implementating #130 | 0:00
| Saturday | 2016-10-01 | 8:00 | 12:47 | 14:05 | 16:00 | Worked on implementating #130 | 2:52
| Sunday | 2016-10-02 | 7:24 | 12:32 | 13:13 | 16:05 | Worked on implementating #130 | 2:16
| Monday | 2016-10-03 | 7:16 | 8:00 | 9:45 | 17:32 |  | -0.29375
| Tuesday | 2016-10-04 | 6:56 | 12:40 | 13:23 | 18:45 | Worked on implementating #130 | 0:22
| Wednesday | 2016-10-05 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Thusday | 2016-10-06 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Friday | 2016-10-07 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
4 | 8 | [6 empty] | 0:00
| Saturday | 2016-10-08 | 7:48 | 13:17 | 13:56 | 16:18 | Diagrams, and started feature document for #142 | 3:07
| Sunday | 2016-10-09 | 8:05 | 12:04 | 13:03 | 15:53 | Worked on implementing #142 | 1:09
| Monday | 2016-10-10 | 6:50 | 7:55 | 9:32 | 19:17 | Worked on implementing #142 | 10:50
| Tuesday | 2016-10-11 | 7:23 | 12:32 | 13:23 | 18:05 | Worked on implementing #142 | 0:27
| Wednesday | 2016-10-12 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Thusday | 2016-10-13 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Friday | 2016-10-14 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| 9 | [6 empty] | 0:00
| Saturday | 2016-10-15 | 8:40 | 12:30 | 13:05 | 17:05 | Diagrams, and started feature document for #204 | 20:55
| Sunday | 2016-10-16 | 7:04 | 12:54 | 13:13 | 16:35 | Worked on implementing #204 | 2:28
| Monday | 2016-10-17 | 7:16 | 8:00 | 10:06 | 17:20 | Worked on implementing #204 | 7:58
| Tuesday | 2016-10-18 | 7:24 | 12:32 | 13:13 | 20:06 | Researched GPS waypoint module needed for upcoming Sprint | 12:01
| Wednesday | 2016-10-19 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Thusday | 2016-10-20 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Friday | 2016-10-21 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
5 | 10 | [6 empty] | 0:00
| Saturday | 2016-10-22 | 8:00 | 12:47 | 14:05 | 16:00 | Worked on implementing #204 | 2:52
| Sunday | 2016-10-23 | 7:24 | 12:32 | 13:13 | 16:05 |  | 2:16
| Monday | 2016-10-24 | 7:16 | 11:54 | 13:02 | 17:32 | Troubleshooted react-native environment issues | 0:08
| Tuesday | 2016-10-25 | 0:00 | 11:00 |  |  | Still troubleshooting react-native environment issues | 11:00
| Wednesday | 2016-10-26 | 2:00 | 12:00 |  |  | Troubleshooted react-native environment issues, field tested on Homestead farm, processed resulting video and navdata results | 10:00
| Thusday | 2016-10-27 |  |  |  |  | Began work on #142 and #204, created design mockups and sequence diagrams | 0:00
| Friday | 2016-10-28 |  |  |  |  | Integrated React-Native theme, continued troubleshooting React-Native environment issues. | 0:00
| 11 | [6 empty] | 0:00
| Saturday | 2016-10-29 | 9:00 | 13:45 | 14:10 | 15:31 | Resolve React-Native environment issues. Continued work on #142. | 3:24
| Sunday | 2016-10-30 | 8:23 | 12:32 | 13:13 | 16:05 | Continued work on #142. | 1:17
| Monday | 2016-10-31 | 7:55 | 11:20 | 12:32 | 16:32 | Stopped work on #142, and #204, shelved code, moved to backlog after instructor recommended against working on any user stories that involved user interface until the rest of the system was built. Informed team of the decision, reorganized Mingle to reflect the change in priorities. | -0.024306
| Tuesday | 2016-11-01 | 7:03 | 12:32 | 13:13 | 16:05 | Worked with Gabriel on server architecture installation. | 2:37
| Wednesday | 2016-11-02 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Thusday | 2016-11-03 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Friday | 2016-11-04 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
6 | 12 | [6 empty] | 0:00
| Saturday | 2016-11-05 | 8:13 | 13:45 | 14:21 | 16:00 | Began work on #131, created sequence diagram | 3:53
| Sunday | 2016-11-06 | 9:21 | 12:02 | 13:04 | 15:19 | Continued work on implementation for #131 | 0:26
| Monday | 2016-11-07 | 6:52 | 10:03 | 23:08 | 16:03 | Continued work on implementation for #131 | 10:16
| Tuesday | 2016-11-08 | 8:12 | 23:46 | 13:42 | 17:21 | Continued work on implementation for #131 | 11:55
| Wednesday | 2016-11-09 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Thusday | 2016-11-10 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Friday | 2016-11-11 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
7 | 13 | [6 empty] | 0:00
| Saturday | 2016-11-12 | 9:23 | 12:05 | 14:01 | 17:06 | Continued work on implementation for #131 | -0.015972
| Sunday | 2016-11-13 | 9:40 | 12:45 | 13:34 | 16:43 | Continued work on implementation for #131 | -0.0027778
| Monday | 2016-11-14 | 8:52 | 10:43 | 12:18 | 17:36 | Continued work on implementation for #131 | -0.14375
| Tuesday | 2016-11-15 | 9:04 | 23:29 | 13:12 | 16:18 | Continued work on implementation for #131 | 11:19
| Wednesday | 2016-11-16 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Thusday | 2016-11-17 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
| Friday | 2016-11-18 |  |  |  |  | No progress today due to my part-time job hours. | 0:00
Formulas:
Date = [Date, row above]+1